## Sheet1
Sr. No.	Designer	Work Task	Work Descriptions	Assign by	assign date	assign time	status	From date	from time	To date	to time	Start date	start time	End date	end time	remarks
	Lavesh Sain	Bug Issue	:: Payroll / 1. Gen Payroll master detail Increment Due Setup, Remminder Setup pages mobile responsive design issue resolve. / :: GENMaster / 1. GEN Master Database New DB Compare Modal Design Issue Resolve With Ravndra Sir. / :: SAGGST / 1. SAGGST GSTR-01 Summary Design Issue Resolve With Piyush Koshik.	Piyush Koshik/ Ravindra Sir	1 Apr 20	9.30am	Done	1 Apr 20	9.30am	1 Apr 20	7.00pm	1 Apr 20	9.30am	1 Apr 20		1.Payroll Increment Due Setup, Reminder Setup Pages Work Complete, 2. SAGGST GSTR-01 Summary Page Work Complete, 3. Master DB Compare page work Complete
	Deepak Jangid	Json work language translate	genmaster language translate	Ujagar sir	1 Apr 20	9.30am	inprogress	1 Apr 20	10.00 AM	1 Apr 20	07:14:00 PM	1 Apr 20	010::00 AM	1 Apr 20		gen master tooptip_key.json and / translate_key.json pr 50% work in hindi
	Kalpna Sharma					9.30am
	Varun Jain	Language Translation and Tooltip	working of grid translation, tooltip integration with language translation	Deepak Sir	1 Apr 20	9.30am	In Progress	1 Apr 20	09:30:00 AM	1 Apr 20	07:30:00 PM	1 Apr 20	09:30:00 AM	1 Apr 20	07:30:00 PM
	Faizan Khan	Make New Login Page Design	All about designing	Ujagar sir	1 Apr 20	9.30am	inprogress	1 Apr 20	09:08:00 AM	1 Apr 20		1 Apr 20	10:00:00 AM	1 Apr 20
	Lavesh Sain	Bug Issue	:: Payroll / 1. Gen Payroll Document Manager Page Make Html Design and modal add. / 2. Gen Payroll Document Manager Page Angular 7 routing Add. / :: GST / 1. GST Old GST Alert Design issue Resolve.	Raj Sir/ Mafar Sir	2 Apr 20	9.30am	Done	2 Apr 20	9.30am	2 Apr 20	7.00pm	2 Apr 20	9.30am	2 Apr 20		1.Payroll Document Manager Pages Work Complete, 2. GST Alert Modal Work Complete,
	Deepak Jangid	Json work language translate	genmaster language translate	Ujagar sir	2 Apr 20	9.30am	Done	2 Apr 20	09:29:00 AM	2 Apr 20	07:30:00 PM	2 Apr 20		2 Apr 20	07:30:00 PM	mohit sir system company law form_gnl1 design issue fix (2 hours) / make 2 modal design in payroll (2 hours) / gen master tooptip_key.json and / translate_key.json work Done in hindi (5 hours and 30 min)
	Kalpna Sharma	New Design	input credit ledger>payment page create and / old gst gstr1 Model Issue solved ajay sir system	anshu mam & Ajay Sir	2 Apr 20	9.30am	Done	2 Apr 20	9.30Am	2 Apr 20	7.10PM	2 Apr 20		2 Apr 20
	Varun Jain	Language Translation and Tooltip	Combining tooltip with language json file, writing function for tooltip integration	Deepak Sir	2 Apr 20	9.30am	In Progress	2 Apr 20	09:30:00 AM	2 Apr 20	07:30:00 PM	2 Apr 20	09:30:00 AM	2 Apr 20	07:30:00 PM
	Faizan Khan	Make New Login Page Design	All about designing		2 Apr 20	9.30am	inprogress	2 Apr 20	09:09:00 AM	2 Apr 20		2 Apr 20		2 Apr 20
	Lavesh Sain	Bug Issue	:: Master / 1. Master Database DB Compare Tool Page Design Make and issue fixed with puneet sir. / :: GST / 1. GST Old Release note entery text fill area issue resolve.	Ribhu Sir/ Puneet Sir/ Ravindra Sir	3 Apr 20	9.30am	Done	3 Apr 20	9.30am	3 Apr 20	7.00pm	3 Apr 20	9.30am	3 Apr 20		1.GST Release Note Entry Pages Work Complete, 2. Master DB Compare page work Complete
	Deepak Jangid	company law, gengst, json work	mohit sir system design issue fixed / Manisha mem system design make 1 modal in gengs / gen master tooptip_key.json in gujarati	mohit sir / Manisha mem	3 Apr 20	9.30am	Done	3 Apr 20	09:28:00 AM	3 Apr 20	07:34:00 PM	3 Apr 20		3 Apr 20	07:34:00 PM	mohit sir system design issue fixed (2 hours) / Manisha mem system design make 1 modal in gengst (2 hours) / gen master tooptip_key.json and / work Done in gujarati (5 hours and 30 min)
	Kalpna Sharma	New Design	input credit ledger work complete & ajay sir / sytem design issue bug fix and ribhu sytem / Design work	anshu mam	3 Apr 20	9.30am	Done	3 Apr 20	9.30Am	3 Apr 20	7.10PM	3 Apr 20		3 Apr 20
	Varun Jain	Language Translation and Tooltip	created shared module for language and ngx tooltip, configuring tooltip on ujagar's computer, debugging errors	Deepak Sir	3 Apr 20	9.30am	In Progress	3 Apr 20	09:30:00 AM	3 Apr 20	07:30:00 PM	3 Apr 20	09:30:00 AM	3 Apr 20	07:30:00 PM
	Faizan Khan	Make New Login Page Design	All about designing		3 Apr 20	9.30am	inprogress	3 Apr 20	09:29:00 AM	3 Apr 20		3 Apr 20		3 Apr 20
	Lavesh Sain				4 Apr 20	9.30am		4 Apr 20		4 Apr 20		4 Apr 20		4 Apr 20
	Deepak Jangid					9.30am
	Kalpna Sharma	New Design	maffer sir work ajay sir sytem	maffer sir	4 Apr 20	9.30am	Done	4 Apr 20	9.30Am	4 Apr 20	7.10PM	4 Apr 20		4 Apr 20
	Varun Jain	Dropdown button on Click	Worked on dropdown button, removed useless and unnecessary css, made button clickable, gstr-01 → fillform – all	Deepak Sir	4 Apr 20	9.30am	In Progress	4 Apr 20	09:30:00 AM	4 Apr 20	07:30:00 PM	4 Apr 20	09:30:00 AM	4 Apr 20	07:30:00 PM
	Faizan Khan	Make New Login Page Design	All about designing and , issue solve ramroop sir system		4 Apr 20	9.30am	Done	4 Apr 20	09:25:00 AM	4 Apr 20		4 Apr 20		4 Apr 20	05:00:00 PM
		Sunday			5 Apr 20	9.30am		5 Apr 20		5 Apr 20		5 Apr 20		5 Apr 20
	Lavesh Sain	Bug Issue	:: Master / 1. Master Database DB Compare Tool Page Design Make and issue fixed with puneet sir. / :: SAGGST / 1. SAGGST GSTR-01 Import Export popup design issue resolve. / 2. SAGGST GSTR-01 Receiver Supplier form and modal design issue resolve.	Aashish Sir/ Ravindra Sir	6 Apr 20	9.30am	Done	6 Apr 20	9.30am	6 Apr 20	7.00pm	6 Apr 20	9.30am	6 Apr 20		1.SAGGST Receiver Form modal Pages Work Complete, 2. SAGGST GSTR-01 Fillform Page Work Complete, 3. Master DB Compare page work Complete
	Deepak Jangid	Company law, payroll, json work	company law mohit sir system desing issue fixed / make 1 page design in payroll / Gengst translate_key.json work in hindi	mohit sir / Lavesh sir	6 Apr 20	9.30am	Done	6 Apr 20		6 Apr 20		6 Apr 20		6 Apr 20	07:29:00 PM	mohit sir system design issue fixed in company law (2 hours) / make 1 page design in payroll (2:30 hours) / gen master translate_key.json work in hindi (5 hours)
	Kalpna Sharma	New Design	gstr2a design issue solved anshu mam system / Cmp08 design work	anshu mam	6 Apr 20	9.30am	Done	6 Apr 20	9.30Am	6 Apr 20	7.10PM	6 Apr 20		6 Apr 20
	Varun Jain	Dropdown button on Click	created a directive for operating dropdown button, prevent event bubling fromdirective, and published the code	Deepak Sir	6 Apr 20	9.30am	Complete	6 Apr 20	09:30:00 AM	6 Apr 20	07:30:00 PM	6 Apr 20	09:30:00 AM	6 Apr 20	07:30:00 PM
	Faizan Khan	Gengst json translate work	tooltip and translte key json translate work (In urdu)		6 Apr 20	9.30am	inprogress	6 Apr 20	09:10:00 AM	6 Apr 20		6 Apr 20	10:45:00 AM	6 Apr 20
	Lavesh Sain	Bug Issue	:: Master / 1. Master Database DB Compare Tool Page Design Make and issue fixed with puneet sir. / :: SAGGST / 1. SAGGST GSTR-01 B2CSA Common serch modal design Issue resolve. / 2. SAGGST GSTR-01 Receiver form HSN Modal Grid Design Issue Resolve. / 3. SAGGST Return GSTR-01 Compare with GSTR-3B page Design Issue Resolve with piyush jain.	Aashish Sir/ Piyush Jain/ Ravindra Sir	7 Apr 20	9.30am	Done	7 Apr 20	9.30am	7 Apr 20	7.00pm	7 Apr 20	9.30am	7 Apr 20		1.SAGGST Receiver Form modal Pages Work Complete, 2. SAGGST GSTR-01 B2CSA Page Work Complete, 3. Master DB Compare page work Complete, 4. SAGGST GSTR-01 Client page modal work complete
	Deepak Jangid	Json work	Gengst tooltip_key.json work in hindi	Ujagar sir	7 Apr 20	9.30am	Done	7 Apr 20		7 Apr 20	07:01:00 PM	7 Apr 20		7 Apr 20	07:01:00 PM	gen master tooltip_key.json work Done in hindi
	Kalpna Sharma	New Design	cmp model create and design bug fix	lovlish sir	7 Apr 20	9.30am	Done	7 Apr 20	9.30Am	7 Apr 20	7.10PM	7 Apr 20		7 Apr 20
	Varun Jain	Language Translation and Tooltip	resolved issue of translate language. Language was resetting automatically after reloading page, implemented in ujagar's pc, figured out an issue of not working language translation in some lazy moduled component	Deepak Sir	7 Apr 20	9.30am	In Progress	7 Apr 20	09:30:00 AM	7 Apr 20	07:30:00 PM	7 Apr 20	09:30:00 AM	7 Apr 20	07:30:00 PM
	Faizan Khan	Gengst json translate work	tooltip and translte key json translate work (In urdu)		7 Apr 20	9.30am	done	7 Apr 20	09:39:00 AM	7 Apr 20		7 Apr 20		7 Apr 20	07:41:00 PM
	Lavesh Sain	Bug Issue	:: Master / 1. Master Database DB Compare Tool Page Design Make and issue fixed with puneet sir. / :: XBRL / 1. XBRL Xbrl As Client Data page design issue resolve With Lalit Singh .	Lalit Sir/ Ravindra Sir	8 Apr 20	9.30am	Done	8 Apr 20	9.30am	8 Apr 20	7.00pm	8 Apr 20	9.30am	8 Apr 20		1. XBRL as Client Database Pages Work Complete, 2. Master DB Compare page work Complete
	Deepak Jangid	company law, gengst, json work	company law lalit sir system design issue fixed / gen gst translate_Key.json in gujarati		8 Apr 20	9.30am	Done	8 Apr 20	09:34:00 AM	8 Apr 20	07:42:00 PM	8 Apr 20		8 Apr 20	07:42:00 PM	Company law design issue fixed (lalit sir) / gen master translate_Key.json in gujarati done
	Kalpna Sharma	New Design	anshu mam input crdit ledger design bugs set and chetan 9a design / Issue bug fix	anshu mam & Chetan sir	8 Apr 20	9.30am	Done	8 Apr 20	9.30Am	8 Apr 20	7.10PM	8 Apr 20		8 Apr 20
	Varun Jain	Focus and Cursor Movement on Grid	Written code for cursor movement in grid from tab and shift tab keys, on gopal ji pc, resolved language translation work on ujagar's pc,	Deepak Sir	8 Apr 20	9.30am	In Progress	8 Apr 20	09:30:00 AM	8 Apr 20	07:30:00 PM	8 Apr 20	09:30:00 AM	8 Apr 20	07:30:00 PM
	Faizan Khan	Gengst json translate work	tooltip and translte key json translate work (In malyalam)		8 Apr 20	9.30am	inprogress	8 Apr 20	09:12:00 AM	8 Apr 20		8 Apr 20	10:50:00 AM	8 Apr 20
	Lavesh Sain	Bug Issue	:: Master / 1. Master Database DB Compare Tool Page Design Make and issue fixed with puneet sir. / ::XBRL / 1. XBRL Xbrl As Client Data page design issue resolve With Lalit Singh . / :: SAGGST / 1. SAGGST GSTR-01 B2CSA Entry Mode Design issue Resolve.	Lalit Sir/ Ravindra Sir/ Aashish Sir	9 Apr 20	9.30am	Done	9 Apr 20	9.30am	9 Apr 20	7.00pm	9 Apr 20	9.30am	9 Apr 20		1. XBRL as Client Data Pages Work Complete, 2. Master DB Compare page work Complete, 3. SAGGST B2CSA Page Entry mode Work Complete.
	Deepak Jangid	company law payroll, mohit sir issue	company law lalit sir system design issue fixed / company law mohit sir system design issue fixed / payroll make 2 modal desing html	mohit sir / lalit sir / Lavesh sir	9 Apr 20	9.30am	Done	9 Apr 20	09:30:00 AM	9 Apr 20	07:34:00 PM	9 Apr 20		9 Apr 20	07:34:00 PM	company law lalit sir system design issue fixed / Company law mohit sir system design issue fixed / payroll make 2 modal desing html
	Kalpna Sharma	New Design	input credit ledger design issue fix anshu mam system and / New design create purchase summay design create	anshu mam	9 Apr 20	9.30am	Done	9 Apr 20	9.30Am	9 Apr 20	7.10PM	9 Apr 20		9 Apr 20
	Varun Jain	Focus and Cursor Movement on Grid	Worked on tab move in grid and change value of select option on up and down arrow keys, default browser functionality , fixed bugs in gridNavigation.js for cursor movement,	Deepak Sir	9 Apr 20	9.30am	In Progress	9 Apr 20	09:30:00 AM	9 Apr 20	07:30:00 PM	9 Apr 20	09:30:00 AM	9 Apr 20	07:30:00 PM
	Faizan Khan	Gengst json translate work	tooltip and translte key json translate work (In malyalam) issue		9 Apr 20	9.30am	done	9 Apr 20	09:16:00 AM	9 Apr 20		9 Apr 20		9 Apr 20	07:31:00 PM
	Lavesh Sain	Bug Issue	:: Master / 1. Master Database DB Compare Tool Page Design Make and issue fixed with puneet sir. / ::XBRL / 1. XBRL Xbrl As Client Data page design issue resolve With Lalit Singh . / :: Payroll / 1. Payroll Arrer Import page design make and routing add in angular.	Lalit Sir/ Ravindra Sir/ Manoj Sir	10 Apr 20	9.30am	Done	10 Apr 20	9.30am	10 Apr 20	7.00pm	10 Apr 20	9.30am	10 Apr 20		1.Payroll Arrear Import Pages Work Complete, 2. XBRL as Client Data Page Work Complete, 3. Master DB Compare page work Complete
	Deepak Jangid	company law payroll, json work	company law design issue fixed / payrol make 2 modal design for Piyush Sir / gen gst tooltip_key in gujarati	mohit sir / Piyush Sir	10 Apr 20	9.30am	Done	10 Apr 20	09:32:00 AM	10 Apr 20	07:59:00 PM	10 Apr 20		10 Apr 20	07:59:00 PM	company law design issue fixed / payrol make 2 modal design for Piyush Sir / gen gst tooltip_key in gujarati
	Kalpna Sharma	New Design	gstr9 and 9c design bug fix / Gstr9a start work	lovlish sir & prakash sir	10 Apr 20	9.30am	Done	10 Apr 20	9.30Am	10 Apr 20	7.10PM	10 Apr 20		10 Apr 20
	Varun Jain	Language Translation and Tooltip	Contacted Punit sir, for figure out issue of language translate on their pc, fixing problem in dropdown button in grid, arrow keys in rate column for dropdown don't execute, resolved issue of language translate in ujagar's pc, debug dropdown promblem of rate column in grid with gopal ji	Deepak Sir	10 Apr 20	9.30am	Complete	10 Apr 20	09:30:00 AM	10 Apr 20	07:30:00 PM	10 Apr 20	09:30:00 AM	10 Apr 20	07:30:00 PM
	Faizan Khan	Gengst json translate work	tooltip and translte key json translate work (In tamil)		10 Apr 20	9.30am	inprogress	10 Apr 20	09:20:00 AM	10 Apr 20		10 Apr 20	10:00:00 AM	10 Apr 20
						9.30am
	lavesh Sain				11 Apr 20	9.30am		11 Apr 20		11 Apr 20		11 Apr 20		11 Apr 20
	Deepak Jangid	genmster json work	genmaster json work	Ujagar sir	11 Apr 20	9.30am	Done	11 Apr 20	09:32:00 AM	11 Apr 20	05:14:00 PM	11 Apr 20		11 Apr 20	05:14:00 PM	gengst Tooltip_Key.json in hindi
	Kalpna Sharma	New Design	eclipse bug come and visual studio bug come	ajay sir & deepak	11 Apr 20	9.30am	Done	11 Apr 20	9.30Am	11 Apr 20	7.10PM	11 Apr 20		11 Apr 20
	Varun Jain	Focus and Cursor Movement on Grid	resolved issue of full screen directive of Piyush Jain, worked on cursor movement on grid on dropdown element of rate column, applied language directive on deepak sir pm and piyush, for commit	Deepak Sir	11 Apr 20	9.30am	In Progress	11 Apr 20	09:30:00 AM	11 Apr 20	07:30:00 PM	11 Apr 20	09:30:00 AM	11 Apr 20	07:30:00 PM
		Sunday			12 Apr 20	9.30am		12 Apr 20		12 Apr 20		12 Apr 20		12 Apr 20
	Lavesh Sain	Bug Issue	::XBRL / 1. XBRL Xbrl As Client Data page design issue resolve With Lalit Singh . / :: SAGGST / 1. SAGGST GSTR-01 Reconcilation modal Issue resolve. / 2. SAGGST GSTR-01 Issue Sheet Resolve with tester Aashish Working on.	Lalit Sir/ Piyush Jain/ Aashish Sir	13 Apr 20	9.30am	Done	13 Apr 20	9.30am	13 Apr 20	7.00pm	13 Apr 20	9.30am	13 Apr 20		1. SAGGST GSTR-01 Reconcilation modal Pages Work Complete, 2. XBRL as Client Data Page Work Complete, 3. SAGGST GSTR-01 Issue Sheet work On.
	Deepak Jangid	company law and gen gst, json work	company law design issue fixed / gen gst make 2 modal design for Manisha mem / gen gst translate_key in marati	lalit sir / Manisha mem	13 Apr 20	9.30am	Done	13 Apr 20	09:37:00 AM	13 Apr 20	07:34:00 PM	13 Apr 20		13 Apr 20	07:34:00 PM	company law design issue fixed / gen gst make 2 modal design for Manisha mem / gen gst translate_key in marati
	Kalpna Sharma	New Design	eclipse bug come and visual studio bug fix by / vikash sir nd gtr9a start work	ajay sir and vikash sir	13 Apr 20	9.30am	Done	13 Apr 20	9.30Am	13 Apr 20	7.10PM	13 Apr 20		13 Apr 20
	Varun Jain	Focus and Cursor Movement on Grid	Written code for cursor movement in grid from tab and shift tab keys, design code to stay focus on grid cell of rate column, with gopal ji	Deepak Sir	13 Apr 20	9.30am	In Progress	13 Apr 20	09:30:00 AM	13 Apr 20	07:30:00 PM	13 Apr 20	09:30:00 AM	13 Apr 20	07:30:00 PM
	Faizan Khan	Gengst json translate work	tooltip and translte key json translate work (In kannada)		13 Apr 20	9.30am	inprogress	13 Apr 20	09:29:00 AM	13 Apr 20		13 Apr 20	10:50:00 AM	13 Apr 20
	Lavesh Sain	Bug Issue	:: SAGGST / 1. SAGGST GSTR-01 Fillform import Export modal design issue resolve with piyush koshik. / 2. SAGGST GSTR-01 Issue Sheet Resolve with tester Aashish Working on.	Piyush Koshik/ Aashish Sir	14 Apr 20	9.30am	Done	14 Apr 20	9.30am	14 Apr 20	7.00pm	14 Apr 20	9.30am	14 Apr 20		1. SAGGST GSTR-01 Fillform Pages Work Complete, 2. SAGGST GSTR-01 Issue Sheet work On.
	Deepak Jangid	company law and gen gst, json work	company law design issue fixed / gen gst translate_key in marati	lalit sir	14 Apr 20	9.30am	Done	14 Apr 20	09:22:00 AM	14 Apr 20	07:30:00 PM	14 Apr 20		14 Apr 20	07:30:00 PM	company law design issue fixed / gen gst tooltip_key in marati
	Kalpna Sharma	New Design	gstr9a design create	lovlish sir	14 Apr 20	9.30am	Done	14 Apr 20	9.30Am	14 Apr 20	7.10PM	14 Apr 20		14 Apr 20
	Varun Jain	Focus and Cursor Movement on Grid	working on dropdown list for those columns who change or update row, after value change. forwarded program for further commit with krishna gopal ji, discussed with ujagar sir about language translate work	Deepak Sir	14 Apr 20	9.30am	Complete	14 Apr 20	09:30:00 AM	14 Apr 20	07:30:00 PM	14 Apr 20	09:30:00 AM	14 Apr 20	07:30:00 PM
	Faizan Khan	Gengst json translate work	tooltip and translte key json translate work (In kannada)		14 Apr 20	9.30am	done	14 Apr 20	09:30:00 AM	14 Apr 20		14 Apr 20		14 Apr 20	07:30:00 PM
	Lavesh Sain	Bug Issue	::Payroll / 1. Payroll Salary PF Arrear modal Popup Design make and Issue Resolve with manoj. / :: SAGGST / 1. SAGGST GSTR-01 Issue Sheet Resolve with tester Aashish Working complete.	Manoj Sir/ Aashish Sir	15 Apr 20	9.30am	Done	15 Apr 20	9.30am	15 Apr 20	7.00pm	15 Apr 20	9.30am	15 Apr 20		1. Payroll PF Arrear Pages Work Complete, 2. SAGGST GSTR-01 Issue Sheet work On.
	Deepak Jangid	payroll, gengst	payroll make modal and gen gst make modal	lavesh sir / Manisha mem	15 Apr 20	9.30am	inprogress	15 Apr 20	09:27:00 AM	15 Apr 20	07:21:00 PM	15 Apr 20		15 Apr 20	07:21:00 PM	payroll make 1 modal (Done) / Gengst (gstr 3b make 2 modal)
	Kalpna Sharma	New Design	gstr9a design create & gstr9c auditor tab design crate	lovlish sir and prakash sir	15 Apr 20	9.30am	Done	15 Apr 20	9.30Am	15 Apr 20	7.10PM	15 Apr 20		15 Apr 20
	Varun Jain					9.30am
	Faizan Khan	Gengst json translate work	tooltip and translte key json translate work (In bangla)		15 Apr 20	9.30am	inprogress	15 Apr 20	09:09:00 AM	15 Apr 20		15 Apr 20	10:00:00 AM	15 Apr 20
	Lavesh Sain				16 Apr 20	9.30am
	Deepak Jangid	New Theme	New Theme Design	Ujagar	16 Apr 20	9.30am
	Kalpna Sharma				16 Apr 20	9.30am
	Varun Jain	Conform Box in New Project.	Confirm Box in Anguarl 7 for every project.	Ujagar	16 Apr 20	9.30am		16 Apr 20	9.30am	16 Apr 20	7.30am
	Faizan Khan	New Theme	New Theme Design	Ujagar	16 Apr 20	9.30am
						9.30am
	Lavesh Sain	Payroll Stop Payment Page Design, Issue		Manoj	17 Apr 20	9.30am		17 Apr 20	9.30Am	17 Apr 20	1.30am
		Gst Return Gstr-01 Email Modal design and Issue Resolve		Piyush	17 Apr 20	9.30am		17 Apr 20	02:00:00 PM	17 Apr 20	7.30am
	Deepak Jangid				17 Apr 20	9.30am		17 Apr 20		17 Apr 20
	Kalpna Sharma				17 Apr 20	9.30am		17 Apr 20		17 Apr 20
	Varun Jain				17 Apr 20	9.30am		17 Apr 20		17 Apr 20
	Faizan Khan				17 Apr 20	9.30am		17 Apr 20		17 Apr 20

	Lavesh Sain	Responsive		ujagar	20 Apr 20	9.30am		20 Apr 20	9.30am	27 Apr 20	7.00pm
		Master Database DB Compare tool Design issue		Raviindra	20 Apr 20	9.30am		20 Apr 20	9.30am	20 Apr 20	01:30:00 PM

	Deepak Jangid	New Theme		Ujagar	20 Apr 20	9.30am		20 Apr 20	9.30am	27 Apr 20	7.00pm
	Kalpna Sharma	Efile & summary page create in gstr9a nd gstr2a design issue		Chetan and Anshu Mam	20 Apr 20	9.30am		20 Apr 20	9.30am	20 Apr 20	7.00pm
	Varun Jain	Responsive Menu and BreadCrumb		ujagar	20 Apr 20	9.30am		20 Apr 20	9.30am	20 Apr 20	2.00pm
	Faizan Khan	New Theme		ujagar	20 Apr 20	9.30am		20 Apr 20	9.30am	27 Apr 20	7.00pm